## EX5311 (hidden)
Tech ID | EX5311 |  |  | Model | 133 | Economic life | 47587
Equipment # | 5311 |  |  | Manufacturer | HITACHI | Projected Annual Utilisation | 2400
Description | Hitachi,EX1200-5M,Excavator,120t |  |  | Plant | Unallocated Equipment Register | Total Frame Hours | 45475
# Components | 39 |  |  | Site Labour Rate | 1 | Current SMU | 38437
Status | Active |  |  | External Labour Rate | 1 | SMU Reading Date | 2022-04-01
Equipment Model Code | System Code | Activity Code | Position Modifier Code | Activity Description |  | Comment | Replacement Total Frame Hours | Replacement Date | Actual Labour Hours | Actual Downtime Hours | Current Component Hours | OEM Target Frequency | Golding Target Frequency | Equipment Target Frequency | Basis for Replacement | Classification | Hours to Run | Next Change Date | Change Date Type | Estimated Component Cost | Estimated Parts Cost | Estimated Service Cost | Labour | Estimated Labour Hours | Estimated Downtime Hours | Estimated Total Cost
133 | BBB | 6510 |  | BUCKET REPAIRS |  |  | 34900 | 2016-07-01 | 0 | 0 | 10575 | 14000 | 20000 |  | Condition | CapEx | 9425 | 2026-03-04 | Estimated | 50000 | 10000 | 10000 | External | 60 | 0 | 70060
133 | UNC | 4157 | LHS | TRACK TENSIONER |  |  | 42469 | 2020-03-10 | 0 | 0 | 3006 | 20000 | 20000 |  | Hours - Flexible | OpEx | 16994 |  | Estimated | 19766 | 0 | 1500 | External | 36 | 0 | 21302
133 | UNC | 4188 | RHS | TRACK ROLLER GROUP |  |  | 42469 | 2020-03-10 | 0 | 0 | 3006 | 20000 | 20000 |  | Condition | OpEx | 16994 |  | Estimated | 27423 | 1500 | 0 | External | 32 | 0 | 28955
133 | UNC | 4188 | LHS | TRACK ROLLER GROUP |  |  | 43117 | 2020-07-12 | 28 | 0 | 2358 | 20000 | 20000 |  | Condition | OpEx | 17642 |  | Estimated | 27423 | 1500 | 0 | External | 32 | 0 | 28955
133 | UNC | 4159 | RHS | IDLER |  |  | 34947 | 2016-07-01 | 0 | 0 | 10528 | 20000 | 20000 |  | Condition | OpEx | 9472 | 2026-03-12 | Estimated | 16165.05 | 0 | 1000 | External | 24 | 0 | 17189.05
133 | UNC | 4159 | LHS | IDLER |  |  | 39533 | 2018-10-13 | 0 | 0 | 5942 | 20000 | 20000 |  | Condition | OpEx | 14058 | 2028-02-07 | Estimated | 16165.05 | 0 | 1000 | External | 24 | 0 | 17189.05
133 | HYD | 4351 | RHS | TRAVEL MOTOR |  |  | 42469 | 2020-03-10 | 0 | 0 | 3006 | 18000 | 18000 |  | Hours - Flexible | OpEx | 14994 |  | Estimated | 17480 | 704.78 | 500 | Site | 12 | 0 | 18696.78
133 | HYD | 4351 | LHS | TRAVEL MOTOR |  |  | 42469 | 2020-03-10 | 0 | 0 | 3006 | 18000 | 18000 |  | Hours - Flexible | OpEx | 14994 |  | Estimated | 17480 | 704.78 | 500 | Site | 12 | 0 | 18696.78
133 | UNC | 4157 | RHS | TRACK TENSIONER |  |  | 42469 | 2020-03-10 | 0 | 0 | 3006 | 20000 | 20000 |  | Hours - Flexible | OpEx | 16994 |  | Estimated | 19766 | 0 | 1500 | External | 36 | 0 | 21302
133 | PWT | 4050 | RHS | FINAL DRIVE |  |  | 26456 | 2011-08-01 | 0 | 0 | 19019 | 18000 | 18000 |  | Hours - Flexible | CapEx | -1019 | 2021-10-28 | Estimated | 42226.77 | 200 | 2500 | External | 24 | 0 | 44950.77
133 | PWT | 3053 |  | TRANSMISSION PUMP |  |  | 32888 | 2013-02-28 | 0 | 0 | 12587 | 0 | 12500 |  | Hours - Flexible | OpEx | -87 | 2022-03-19 | Estimated | 6500 | 100 | 0 | Site | 8 | 0 | 6608
133 | HYD | 5058 | RER | SWING MOTOR |  |  | 42002 | 2019-11-11 | 0 | 0 | 3473 | 12000 | 12000 |  | Hours - Flexible | OpEx | 8527 | 2025-10-19 | Estimated | 13744.73 | 200 | 500 | Site | 12 | 0 | 14456.73
133 | HYD | 5058 | FRT | SWING MOTOR |  |  | 33585 | 2013-08-01 | 0 | 0 | 11890 | 12000 | 12000 |  | Hours - Flexible | OpEx | 110 | 2022-04-18 | Estimated | 13744.73 | 200 | 500 | Site | 12 | 0 | 14456.73
133 | PWT | 5459 | RER | SWING BOX |  |  | 42469 | 2020-03-10 | 0 | 0 | 3006 | 18000 | 18000 |  | Hours - Flexible | CapEx | 14994 |  | Estimated | 29316 | 200 | 1500 | External | 24 | 0 | 31040
133 | PWT | 5459 | FRT | SWING BOX |  |  | 42469 | 2020-03-10 | 0 | 0 | 3006 | 18000 | 18000 |  | Hours - Flexible | CapEx | 14994 |  | Estimated | 29316 | 200 | 1500 | External | 24 | 0 | 31040
133 | PWT | 3108 |  | PUMP DRIVE BOX |  |  | 38897 | 2018-06-15 | 0 | 0 | 6578 | 20000 | 20000 |  | Hours - Flexible | CapEx | 13422 | 2027-11-02 | Estimated | 35291 | 5488.06 | 2000 | External | 24 | 0 | 42803.06
133 | ENG | 1353 |  | RADIATOR |  |  | 38897 | 2018-06-15 | 0 | 0 | 6578 | 20000 | 20000 |  | Hours - Flexible | CapEx | 13422 | 2027-11-02 | Estimated | 64535 | 2498 | 1500 | External | 24 | 0 | 68557
133 | PWT | 4050 | LHS | FINAL DRIVE |  |  | 36267 | 2017-02-01 | 0 | 0 | 9208 | 18000 | 18000 |  | Hours - Flexible | CapEx | 8792 | 2025-11-28 | Estimated | 42226.77 | 200 | 2500 | External | 24 | 0 | 44950.77
133 | ENG | 1001 |  | ENGINE MIDLIFE |  | already set correctly | 28897 | 2016-12-24 | 0 | 0 | 16578 | 20000 | 20000 |  | Hours - Flexible | OpEx | 3422 | 2023-09-03 | Estimated | 0 | 35439 | 0 | External | 42 | 0 | 35481
133 | UNC | 4170 | LHS | TRACK |  |  | 43117 | 2020-07-12 | 39 | 0 | 2358 | 20000 | 20000 |  | Condition | OpEx | 17642 |  | Estimated | 48558 | 0 | 4000 | Site | 12 | 0 | 52570
133 | HYD | 5084 | P01 | IMPLEMENT PUMP |  |  | 38897 | 2018-06-15 | 0 | 0 | 6578 | 14000 | 14000 |  | Hours - Flexible | OpEx | 7422 | 2025-05-04 | Estimated | 24124 | 500 | 1000 | External | 24 | 0 | 25648
133 | CHA | 7063 |  | SLEW BEARING | [6 empty] | 45475 | 25000 | 25000 |  | Condition | CapEx | -20475 | 2013-09-21 | Estimated | 57371 | 500 | 35000 | External | 216 | 0 | 93087
133 | CHA | 6551 |  | BOOM PINS & BUSHES |  |  | 44828 | 2021-08-10 | 245 |  | 647 | 14000 | 14000 |  | Condition | OpEx | 13353 | 2027-10-23 | Estimated | 0 | 15829 | 1500 | External | 124 | 0 | 17453
133 | CHA | 6550 |  | ARM PINS & BUSHES |  |  | 44828 | 2021-08-10 | 0 |  | 647 | 16000 | 16000 |  | Condition | OpEx | 15353 |  | Estimated | 0 | 33201 | 1500 | External | 32 | 0 | 34733
133 | CHA | 6549 |  | BUCKET PINS & BUSHES |  |  | 44828 | 2021-08-10 | 94 |  | 647 | 9000 | 9000 |  | Condition | OpEx | 8353 | 2025-09-22 | Estimated | 0 | 22370 | 0 | External | 72 | 0 | 22442
133 | HYD | 1398 |  | HYDRAULIC COOLER FAN MOTOR |  |  | 32888 | 2013-02-20 | 0 | 0 | 12587 | 15000 | 15000 |  | Hours - Flexible | OpEx | 2413 | 2023-04-03 | Estimated | 6487.09 | 2072.45 | 0 | Site | 12 | 0 | 8571.54
133 | HYD | 1374 |  | HYDRAULIC OIL COOLER |  |  | 35659 | 2016-11-14 | 0 | 0 | 9816 | 20000 | 20000 |  | Hours - Flexible | OpEx | 10184 | 2026-06-28 | Estimated | 16578 | 886.86 | 1000 | External | 20 | 0 | 18484.86
133 | HYD | 5457 |  | BUCKET CYLINDER |  |  | 42468 | 2020-03-13 | 0 | 0 | 3007 | 8000 | 8000 |  | Hours - Flexible | CapEx | 4993 | 2024-04-29 | Estimated | 39943.89 | 300 | 1000 | External | 24 | 0 | 41267.89
133 | UNC | 4170 | RHS | TRACK |  |  | 43117 | 2020-07-12 | 39 | 0 | 2358 | 20000 | 20000 |  | Condition | OpEx | 17642 |  | Estimated | 48558 | 0 | 4000 | Site | 12 | 0 | 52570
133 | HYD | 5458 |  | ARM CYLINDER |  |  | 44735 | 2021-07-13 | 19 |  | 740 | 10000 | 10000 |  | Hours - Flexible | CapEx | 9260 | 2026-02-07 | Estimated | 42959 | 5571.99 | 1000 | External | 24 | 0 | 49554.99
133 | HYD | 5456 | LHS | BOOM CYLINDER |  |  | 34255 | 2016-01-01 | 0 | 0 | 11220 | 10000 | 10000 |  | Hours - Flexible | CapEx | -1220 | 2021-09-27 | Estimated | 40888.43 | 6839.65 | 1000 | External | 24 | 0 | 48752.08
133 | HYD | 5051 | RHS | MAIN CONTROL VALVE |  |  | 24115 | 2011-01-28 | 0 | 0 | 21360 | 24000 | 24000 |  | Condition | OpEx | 2640 | 2023-05-08 | Estimated | 27486 | 500 | 1000 | Site | 16 | 0 | 29002
133 | HYD | 5051 | LHS | MAIN CONTROL VALVE |  |  | 24115 | 2011-01-28 | 0 | 0 | 21360 | 24000 | 24000 |  | Condition | CapEx | 2640 | 2023-05-08 | Estimated | 54640 | 500 | 1000 | External | 24 | 0 | 56164
133 | HYD | 5085 |  | PILOT PUMP |  |  | 41326 | 2019-08-16 | 0 | 0 | 4149 | 14000 | 14000 |  | Hours - Flexible | OpEx | 9851 | 2026-05-08 | Estimated | 4147 | 100 | 0 | Site | 8 | 0 | 4255
133 | HYD | 5049 |  | HYDRAULIC COOLER FAN PUMP |  |  | 32888 | 2013-02-28 | 0 | 0 | 12587 | 14000 | 14000 |  | Hours - Flexible | OpEx | 1413 | 2022-11-02 | Estimated | 13444 | 500 | 0 | Site | 12 | 0 | 13956
133 | HYD | 5084 | P03 | IMPLEMENT PUMP |  |  | 32888 | 2013-02-28 | 0 | 0 | 12587 | 14000 | 14000 |  | Hours - Flexible | OpEx | 1413 | 2022-11-02 | Estimated | 24124 | 500 | 1000 | External | 24 | 0 | 25648
133 | HYD | 5084 | P02 | IMPLEMENT PUMP |  |  | 38897 | 2018-06-15 | 0 | 0 | 6578 | 14000 | 14000 |  | Hours - Flexible | OpEx | 7422 | 2025-05-04 | Estimated | 24124 | 500 | 1000 | External | 24 | 0 | 25648
133 | HYD | 5456 | RHS | BOOM CYLINDER |  |  | 36684 | 2017-05-12 | 0 | 0 | 8791 | 10000 | 10000 |  | Hours - Flexible | CapEx | 1209 | 2022-10-02 | Estimated | 40888.43 | 6839.65 | 1000 | External | 24 | 0 | 48752.08
133 | ENG | 1000 |  | ENGINE |  |  | 38897 | 2018-06-15 | 0 | 0 | 6578 | 20000 | 20000 |  | Hours - Flexible | CapEx | 13422 | 2027-11-02 | Estimated | 239386 | 7447 | 2000 | External | 92 | 0 | 248925

## EX5314
Tech ID | EX5314 |  |  | Model | 132 | Economic life | 53602
Equipment # | 5314 |  |  | Manufacturer | HITACHI | Projected Annual Utilisation | 2400
Description | Hitachi,EX1200-5C,Excavator,120t |  |  | Plant | Unallocated Equipment Register | Total Frame Hours | 31422
# Components | 39 |  |  | Site Labour Rate | 1 | Current SMU | 17975
Status | Active |  |  | External Labour Rate | 1 | SMU Reading Date | 2022-07-01
Equipment Model Code | System Code | Activity Code | Position Modifier Code | Activity Description |  | Comment | Replacement Total Frame Hours | Replacement Date | Actual Labour Hours | Actual Downtime Hours | Current Component Hours | OEM Target Frequency | Golding Target Frequency | Equipment Target Frequency | Basis for Replacement | Classification | Hours to Run | Next Change Date | Change Date Type | Estimated Component Cost | Estimated Parts Cost | Estimated Service Cost | Labour | Estimated Labour Hours | Estimated Downtime Hours | Estimated Total Cost
132 | BBB | 6510 |  | BUCKET REPAIRS | [6 empty] | 31422 | 14000 | 20000 |  | Condition | CapEx | -11422 | 2017-09-28 | Estimated | 50000 | 10000 | 10000 | External | 60 | 0 | 70060
132 | UNC | 4157 | LHS | TRACK TENSIONER |  |  | 9991 | 2011-06-24 | 0 | 0 | 21431 | 20000 | 20000 |  | Hours - Flexible | OpEx | -1431 | 2021-11-25 | Estimated | 19766 | 0 | 1500 | External | 36 | 0 | 21302
132 | UNC | 4188 | RHS | TRACK ROLLER GROUP |  |  | 26243 | 2019-09-03 | 0 | 0 | 5179 | 20000 | 20000 |  | Condition | OpEx | 14821 |  | Estimated | 27423 | 1500 | 0 | External | 32 | 0 | 28955
132 | UNC | 4188 | LHS | TRACK ROLLER GROUP |  |  | 24654 | 2018-10-26 | 0 | 0 | 6768 | 20000 | 20000 |  | Condition | OpEx | 13232 | 2028-01-03 | Estimated | 27423 | 1500 | 0 | External | 32 | 0 | 28955
132 | UNC | 4159 | RHS | IDLER |  |  | 23409 | 2018-01-06 | 0 | 0 | 8013 | 20000 | 20000 |  | Condition | OpEx | 11987 | 2027-06-28 | Estimated | 16165.05 | 0 | 1000 | External | 24 | 0 | 17189.05
132 | UNC | 4159 | LHS | IDLER |  |  | 26243 | 2019-09-03 | 0 | 0 | 5179 | 20000 | 20000 |  | Condition | OpEx | 14821 |  | Estimated | 16165.05 | 0 | 1000 | External | 24 | 0 | 17189.05
132 | HYD | 4351 | RHS | TRAVEL MOTOR |  |  | 17030 | 2015-02-01 | 0 | 0 | 14392 | 18000 | 18000 |  | Hours - Flexible | OpEx | 3608 | 2024-01-01 | Estimated | 17480 | 704.78 | 500 | Site | 12 | 0 | 18696.78
132 | HYD | 4351 | LHS | TRAVEL MOTOR |  |  | 17030 | 2015-02-01 | 0 | 0 | 14392 | 18000 | 18000 |  | Hours - Flexible | OpEx | 3608 | 2024-01-01 | Estimated | 17480 | 704.78 | 500 | Site | 12 | 0 | 18696.78
132 | UNC | 4157 | RHS | TRACK TENSIONER |  |  | 29296 | 2020-11-27 | 0 | 0 | 2126 | 20000 | 20000 |  | Hours - Flexible | OpEx | 17874 |  | Estimated | 19766 | 0 | 1500 | External | 36 | 0 | 21302
132 | PWT | 4050 | RHS | FINAL DRIVE |  |  | 22514 | 2017-05-28 | 0 | 0 | 8908 | 18000 | 18000 |  | Hours - Flexible | CapEx | 9092 | 2026-04-14 | Estimated | 42226.77 | 200 | 2500 | External | 24 | 0 | 44950.77
132 | PWT | 3053 |  | TRANSMISSION PUMP |  |  | 29439 | 2020-12-14 | 0 | 0 | 1983 | 0 | 12500 |  | Hours - Flexible | OpEx | 10517 | 2026-11-16 | Estimated | 6500 | 100 | 0 | Site | 12 | 0 | 6612
132 | HYD | 5058 | RER | SWING MOTOR |  |  | 23825 | 2018-05-31 | 0 | 0 | 7597 | 12000 | 12000 |  | Hours - Flexible | OpEx | 4403 | 2024-05-01 | Estimated | 13744.73 | 200 | 500 | Site | 12 | 0 | 14456.73
132 | HYD | 5058 | FRT | SWING MOTOR |  |  | 23825 | 2018-05-31 | 0 | 0 | 7597 | 12000 | 12000 |  | Hours - Flexible | OpEx | 4403 | 2024-05-01 | Estimated | 13744.73 | 200 | 500 | Site | 12 | 0 | 14456.73
132 | PWT | 5459 | RER | SWING BOX |  |  | 23825 | 2018-05-31 | 0 | 0 | 7597 | 18000 | 18000 |  | Hours - Flexible | CapEx | 10403 | 2026-10-30 | Estimated | 29316 | 200 | 1500 | External | 24 | 0 | 31040
132 | PWT | 5459 | FRT | SWING BOX |  |  | 26542 | 2019-11-12 | 0 | 0 | 4880 | 18000 | 18000 |  | Hours - Flexible | CapEx | 13120 | 2027-12-17 | Estimated | 29316 | 200 | 1500 | External | 24 | 0 | 31040
132 | PWT | 3108 |  | PUMP DRIVE BOX |  |  | 17030 | 2015-02-01 | 0 | 0 | 14392 | 20000 | 20000 |  | Hours - Flexible | CapEx | 5608 | 2024-10-31 | Estimated | 35291 | 5488.06 | 2000 | External | 24 | 0 | 42803.06
132 | ENG | 1353 |  | RADIATOR |  |  | 17030 | 2015-02-01 | 0 | 0 | 14392 | 20000 | 20000 |  | Hours - Flexible | CapEx | 5608 | 2024-10-31 | Estimated | 64535 | 2498 | 1500 | External | 24 | 0 | 68557
132 | PWT | 4050 | LHS | FINAL DRIVE |  |  | 22514 | 2017-05-28 | 0 | 0 | 8908 | 18000 | 18000 |  | Hours - Flexible | CapEx | 9092 | 2026-04-14 | Estimated | 42226.77 | 200 | 2500 | External | 24 | 0 | 44950.77
132 | ENG | 1001 |  | ENGINE MIDLIFE |  | Se to match theoretical next engine. | 26317 | 2019-09-14 | 0 | 0 | 5105 | 20000 | 20000 | 20713 | Hours - Flexible | OpEx | 15608 |  | Estimated | 0 | 35439 | 0 | External | 42 | 0 | 35481
132 | UNC | 4170 | LHS | TRACK |  |  | 26243 | 2019-09-03 | 0 | 0 | 5179 | 20000 | 20000 |  | Condition | OpEx | 14821 |  | Estimated | 48558 | 0 | 4000 | Site | 12 | 0 | 52570
132 | HYD | 5084 | P01 | IMPLEMENT PUMP |  |  | 24216 | 2018-08-17 | 0 | 0 | 7206 | 14000 | 14000 |  | Hours - Flexible | OpEx | 6794 | 2025-04-29 | Estimated | 24124 | 500 | 1000 | External | 24 | 0 | 25648
132 | CHA | 7063 |  | SLEW BEARING |  |  | 17030 | 2015-02-01 | 0 | 0 | 14392 | 25000 | 25000 |  | Condition | CapEx | 10608 | 2026-11-30 | Estimated | 57371 | 500 | 35000 | External | 216 | 0 | 93087
132 | CHA | 6551 |  | BOOM PINS & BUSHES |  |  | 17030 | 2015-02-01 | 0 | 0 | 14392 | 14000 | 14000 |  | Condition | OpEx | -392 | 2022-05-02 | Estimated | 0 | 15829 | 1500 | External | 124 | 0 | 17453
132 | CHA | 6550 |  | ARM PINS & BUSHES |  |  | 17030 | 2015-02-01 | 0 | 0 | 14392 | 16000 | 16000 |  | Condition | OpEx | 1608 | 2023-03-03 | Estimated | 0 | 33201 | 1500 | External | 80 | 0 | 34781
132 | CHA | 6549 |  | BUCKET PINS & BUSHES |  |  | 29544 | 2021-01-08 |  |  | 1878 | 9000 | 9000 |  | Condition | OpEx | 7122 | 2025-06-18 | Estimated | 0 | 22370 | 0 | External | 72 | 0 | 22442
132 | HYD | 1398 |  | HYDRAULIC COOLER FAN MOTOR |  |  | 23825 | 2018-05-21 | 0 | 0 | 7597 | 15000 | 15000 |  | Hours - Flexible | OpEx | 7403 | 2025-07-31 | Estimated | 6487.09 | 2072.45 | 0 | Site | 12 | 0 | 8571.54
132 | HYD | 1374 |  | HYDRAULIC OIL COOLER |  |  | 24654 | 2018-10-26 | 0 | 0 | 6768 | 20000 | 20000 |  | Hours - Flexible | OpEx | 13232 | 2028-01-03 | Estimated | 16578 | 886.86 | 1000 | External | 20 | 0 | 18484.86
132 | HYD | 5457 |  | BUCKET CYLINDER |  |  | 28636 | 2020-08-04 | 0 | 0 | 2786 | 8000 | 8000 |  | Hours - Flexible | CapEx | 5214 | 2024-09-01 | Estimated | 39943.89 | 300 | 1000 | External | 24 | 0 | 41267.89
132 | UNC | 4170 | RHS | TRACK |  |  | 26243 | 2019-09-03 | 0 | 0 | 5179 | 20000 | 20000 |  | Condition | OpEx | 14821 |  | Estimated | 48558 | 0 | 4000 | Site | 12 | 0 | 52570
132 | HYD | 5458 |  | ARM CYLINDER |  |  | 28636 | 2020-08-02 | 7 | 0 | 2786 | 10000 | 10000 |  | Hours - Flexible | CapEx | 7214 | 2025-07-02 | Estimated | 42959 | 5571.99 | 1000 | External | 24 | 0 | 49554.99
132 | HYD | 5456 | LHS | BOOM CYLINDER |  |  | 28057 | 2020-05-22 | 82 | 0 | 3365 | 10000 | 10000 |  | Hours - Flexible | CapEx | 6635 | 2025-04-05 | Estimated | 40888.43 | 6839.65 | 1000 | External | 24 | 0 | 48752.08
132 | HYD | 5051 | RHS | MAIN CONTROL VALVE |  |  | 8784 | 2017-05-05 | 0 | 0 | 22638 | 24000 | 24000 |  | Condition | OpEx | 1362 | 2023-01-24 | Estimated | 27486 | 500 | 0 | Site | 16 | 0 | 28002
132 | HYD | 5051 | LHS | MAIN CONTROL VALVE |  |  | 8784 | 2017-05-05 | 0 | 0 | 22638 | 24000 | 24000 |  | Condition | CapEx | 1362 | 2023-01-24 | Estimated | 54640 | 500 | 1000 | External | 24 | 0 | 56164
132 | HYD | 5085 |  | PILOT PUMP |  |  | 24216 | 2018-08-17 | 0 | 0 | 7206 | 14000 | 14000 |  | Hours - Flexible | OpEx | 6794 | 2025-04-29 | Estimated | 4147 | 100 | 0 | Site | 8 | 0 | 4255
132 | HYD | 5049 |  | HYDRAULIC COOLER FAN PUMP |  |  | 24216 | 2018-08-17 | 0 | 0 | 7206 | 14000 | 14000 |  | Hours - Flexible | OpEx | 6794 | 2025-04-29 | Estimated | 13444 | 500 | 0 | Site | 12 | 0 | 13956
132 | HYD | 5084 | P03 | IMPLEMENT PUMP |  |  | 23812 | 2018-05-08 | 0 | 0 | 7610 | 14000 | 14000 |  | Hours - Flexible | OpEx | 6390 | 2025-02-27 | Estimated | 24124 | 500 | 1000 | External | 24 | 0 | 25648
132 | HYD | 5084 | P02 | IMPLEMENT PUMP |  |  | 24216 | 2018-08-17 | 0 | 0 | 7206 | 14000 | 14000 |  | Hours - Flexible | OpEx | 6794 | 2025-04-29 | Estimated | 24124 | 500 | 1000 | External | 24 | 0 | 25648
132 | HYD | 5456 | RHS | BOOM CYLINDER |  |  | 28842 | 2020-09-05 | 0 | 0 | 2580 | 10000 | 10000 |  | Hours - Flexible | CapEx | 7420 | 2025-08-02 | Estimated | 40888.43 | 6839.65 | 1000 | External | 24 | 0 | 48752.08
132 | ENG | 1000 |  | ENGINE |  |  | 17030 | 2015-02-01 | 0 | 0 | 14392 | 20000 | 20000 |  | Hours - Flexible | CapEx | 5608 | 2024-10-31 | Estimated | 239386 | 7447 | 2000 | External | 92 | 0 | 248925